Assignment 7: Leadership and Project Management

Predict 475 Project Management

Professor: Dan Roth

Section 55

Winter Quarter

School of Continuing Studies

Northwestern University

Daniel Prusinski

Business Intelligence Data Analyst

Target Corporation

Minneapolis, MN

In Compliance with Master of Science Predictive Analytics

## Table of Contents

Project Scope Statement…………………………………………………………………………3-4

Priority Matrix…………………………………………………………………………..………………5

Communication Objectives.……………………………………………….………..……………6-7

Communication Plan............................................................................……...7

Register………………………………………………………………………………………...8

Appendix 1: Project Proposal……………………………………………………………………9-11

Work Breakdown Structure……..………………………………………………………………...12

Cost and Time Estimate……………………………………………………………..13-15

Activity On Node………………………………………………………………………………………16

Description / Relation to WBS ……………………………………………………………….17-18

Risk Breakdown Structure………………………………………………………………………..19

Risk Assessment Matrix…………………………………………………………………………..19

Risk Severity Matrix………………………………………………………………………………..20

Risk Response Matrix.……………………………………………………………………………..21

Change Control Process…………………………………………………………………………..21

Change Request Form……………………………………………………………………………..22

Human Resources Management Plan…………………………………………………………..23

Schedule Management Plan…………………….…………………………………….…………..26

Appendix 2 Resource Plan…………………….…………………………………….……………..30

Appendix 3 Schedule Budget……………….…………………………………….……..………..32

Appendix 4 Leadership and Project Management Experiences…………………………….34

Executive Summary…………….…………………………………………………….……NA

Gantt chart (Baseline)…………………………………………………………….NA

Feasibility

Integration

Project MetaGuest Scope Statement

1. Project Objective:

Develop an automated, self-emailing, report that focuses specifically on the current state of the Target guest through trending key meta metrics about guest data. The project is to be fully completed, iterated, and user functional by December 2014 and resources are all to be derived internally at Target at no outside additional cost.

2. Deliverables:

MetaGuest is a technical project that is better suited for a process breakdown structure (PBS) broken in to key phases. The deliverables will follow each major phase and are outlined below-

* Analysis – Establish key metrics to be trended overtime, and the time interval for which the analysis will be based. The metrics are not to exceed fifteen an shall have no less than ten in the report.
* Design – Have three different dashboard designs and feedback from key stakeholders and intended users.
* Construct – Final version of code vetted, documented, and synthesized with reoccurring reporting team.
* Test – Run report over four weeks, with at least three participating team member and no more than seven, to assess overall effectiveness as well as make iterations.
* Rollout – Schedule, present, and collect feedback on three different presentations for key stakeholders as well as intended users.

3. Milestones:

In developing important milestones for MetaGuest, natural benchmarks within Target process flow are documented below-

* March 21 - Project Charter Acceptance, Manager
* March 31 – Multi-Department Project Acceptance
* May 14 – Key Metrics Established
* June 14 – Dashboard Design Approved
* July 30 – Final Documentation of Standardized Code
* August 18 – Final Iterations Complete
* September 15 – Presentations
* October 15 – End User Feedback
* November 15 – Hand in Completed Project Documentation

4. Technical Requirements:

Target is in the midst of migrating from an IBM database to Teradata, and will require duplicative coding efforts and specifications in order to meet the project objective within the timeframe

* Establish how stable guest logic will be applied to MetaGuest
* Define where MetaGuest will reside post-project
* Create coding that minimizes creating irrelevant tables
* Define whether excel, SAS, or Tableau is the best dashboard tool
* Reporting requirements must meet specified bandwidth
* Table pulls must follow changing requirements
* Code needs to be written in an EDW and ADW format
* Delivery method must be a push rather than a pull for end users

5. Limits and Exclusions:

In an effort to focus on the expectations of MetaGuest, the limits and exclusions are detailed below:

* MetaGuest will contain only Guest data, and no POS data
* The report is objective across all divisions without customization
* End users are responsible for ad-hoc additional metrics
* Creating a storage repository is not included in MetaGuest
* Intended end users are Guest Insights and Division Insights
* Healthcare data will not be included
* Target Canada data will not be included
* Email notification and centralize posting is the means of delivery

6. Review with Management: James Nelson

Before moving forward, communication and iterations to the project scope statement must be resolved in an effort to be of one accord. Deadline for Review with Management resolve is 1/23/2013.

MetaGuest Priority Matrix

Project efficacy is helpfully demonstrated from the graphic below:

Quality

The priority matrix below details how the three attributes are prioritized.

|  |  |  |  |
| --- | --- | --- | --- |
|  | Time | Performance | Cost |
| Constrain | X |  |  |
| Enhance |  | X |  |
| Accept |  |  | X |

Accept: Tolerable *not* to meet the original parameters.

Enhance: During the project, enhancements can be made to this parameter.

Constrain: This parameter must be met.

MetaGuest Communication Objectives

The project scope statement is the first communication piece that needs to be agreed upon by management. Additional information needed for the success of MetaGuest is detailed below:

Reporting Requirements- Desired metrics, calculations for metrics, and interval requirements need to be gathered in the analysis phase. The project manager will refine the requirements with the key manager and finally communicated to a few of the end users. The information will be stored on the project managers folder on Target’s public hard drive space. Unless noted, the information is public, but does not need to be broadcasted. The final reporting requirements will be communicated with the end users at the end of the analysis phase in the monthly status meeting.

Design Information Communication – The Reporting Team will need to know the established reporting requirements prior designing the report for MetaGuest. A PowerPoint will be assembled by the Project Manager to communicate the reporting requirements, which will be stored in an Excel Table. There are no privacy concerns for the reporting team. The information will be communicated in a presentation with hard copied available and soft copies sent out after the meeting.

Construction Information Communication – Writing the code for MetaGuest will require a few analysts. SAS will be the primary tool for writing the code and communication will be done in person and through email. At this point authors of the code will include James Nelson, Jacob Yunker, Daniel Prusinski, and Senthilkumar Subramanian. It is vital that the code be well documented by each programmer so that collaboration ensues. Weekly iterations will be highlighted in an email with documentation communicating why the changes were necessary.

Testing Information Communication – As the report is tested, users will record comments and suggestive iterations on a provided form electronically. The goal is to have a seamless turnaround time, and not become bogged down with expansive changes. Potential changes will be vetted with management before making final iterations in a meeting with the project manager. The presentation will entail a PowerPoint presentation and soft copy in the form of word document tracking proposed changes.

Rollout Communication – The rollout will take place in a monthly team meeting, and management will introduce MetaReport to the whole team. This will be done in a PowerPoint presentation, and the end users present will get a copy of the actual report during the meeting. At the end of the meeting, the end users will have a physically provided form to fill out seeking feedback and general comments. These comments will be synthesized by the project management into a Word document and shared with the manager in an in person meeting.

Communication Plan

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| What Information | Target Audience | When | Method | Tool for Communication |
| Scope Statement | Project manager, key stakeholders | Once, first week | Email with hardcopy | Word |
| Project Plan | Key stakeholders, management | Once, mid March | Email, hardcopy | Word |
| Key Metric Findings | End Users | Weekly during analysis phase | Email, and presentation | Word, Powerpoint |
| Milestone Update | Project manager, key stakeholders | Biweekly | Email | Office |
| Project Update | Manager | Weekly | In person | Word |
| Cross-functional team update | Reporting, Guest & Division Insights | Monthly | In person meeting | PowerPoint with Word copy |
| Design Template | Manager, End Users | Weekly, during Design Phase | Working meeting, and email | PowerPoint and Word/Tableau |
| Developed Code | Data Analysts | When needed during construct and test phases | Email, text editor | SAS |
| Beta MetaReport | Manager, Testing Team | Weekly during testing phase | Email, in person | SAS, and email dashboard |
| Issues and Delays | Manager, key stakeholdes | When needed | Email and meeting | Word, Office |
| Accepted Changes | Project Manager | When needed | Email or meeting | Word, Office |
| Final Product | End Users, and Management | Weekly, in rollout phase | Email or centralized location | SAS, or Tableau |

MetaGuest Register

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **STAKEHOLDER REGISTER for MetaGuest** | | | | |
|  | **Name** | **Designation/Title** | **Dept** | **Role** | **Interests** |
| **1** | Colleen Theisen | Sr. Manager | MMBI | Manager | Team Head |
| **2** | James Nelson | Manager | MBI | Direct Manager | Key Benefactor |
| **3** | Mark VonOven | Director | BI&A | Key Stakeholder | Next Level of Analytics |
| **4** | Dan Ryks | Reporting Manager | MMBI | Oversees Reporting | Reporting Aspect |
| **5** | Jarrett Reed | Division Insights | MBI | End User | End User |
|  | **Name** | **Type/Frequency of Communication** | **Contact** | **Influence** | **Power** |
| **1** | Colleen Theisen | Email / Monthly | E-mail | Management | Resouce and Authority |
| **2** | James Nelson | In Person / Weekly | E-mail | Resources | Direct Team Authority |
| **3** | Mark VonOven | Written out/ Quarterly | Email | Little | Manages all Aspects of Project |
| **4** | Dan Ryks | Template / Weekly | E-mail | None | Will run future reports |
| **5** | Jarrett Reed | Presentation / Daily | E-mail | Design | Little |
|  | **Name** | **Expectations** | **Internal/External** |  |  |
| **1** | Colleen Theisen | Keep Updated | Internal |  |  |
| **2** | James Nelson | Key Point of Contact | Internal |  |  |
| **3** | Mark VonOven | Only Key Updates | Internal |  |  |
| **4** | Dan Ryks | Build Template | Internal |  |  |
| **5** | Jarrett Reed | Testing and Roll Out | Internal |  |  |

Appendix 1: Project Proposal

Target Corporation is a billion dollar retail company. With over 1,200 stores nationwide, millions of guests shop Target daily. One strategic initiative senior leadership has road-mapped for 2014 is deepening guest engagement. Management within my department, Merchandising and Marketing Business Intelligence (MMBI), has asked me to create a project plan for better defining and monitoring overall guest behavior data at target in the form of a report that shows key metrics about our guests over time.

I will name this project MetaGuest based on the overall desired outcome for information about guest data to be fed to team members in a concise report. As of January 8, 2013 my manager, James Nelson, is the official project sponsor. The current stakeholder groups include the following:

Guest Insights (GI) – Target’s MMBI team that represents guest data.

Division Insights – Similar to GI, but works with merchandising divisional leadership on guest data requests.


Reporting – Coordinates and executes reporting for MBI.

Business Data Quality (BDQ) – Represents Target’s importation and cleaning of data.

Division Insight Leaders (DILs) – Communicate the desired outcomes for guest data.

As Target aims to meet growing consumer demands, understanding changing behaviors aptly translates to thriving and surviving in the retail environment. Currently, Target has built many tools for extracting guest information and classification categories for different types of guests. The next step for Target reaching its goal of deepening guest engagement through data-driven analytics is understanding changes in guest behavior and predicting future outcomes. The overall value project MetaGuest brings is the next step in analytical capability for Target through quantifying guest behavior through time.

The key project constraints at this point include cost, schedule, budget, and resources. Each constraint will require further iterations given that the project is being preliminarily scoped. The costs to Target at this point include no outside purchases of software, consulting, or products, but rather cost internal time, and resources. I would expect two hours a week for 2014 in regard to my personal schedule, as well as 2 hours a week of other team members through the process. Total time cost is estimated at 200 hours. Given that the new reporting to be established will take place within pre-existing innovation space via data tables and software, the costs are considered sunk costs and do not entail an extra cost. Over the next ten weeks further planning of project MetaGuest will take place and implementation will begin four weeks after the project plan is accepted. Preliminarily, March 25th is the planned date to begin implementing the project. Final feedback on the project is expected the first week of October. Please refer to the diagram below for a more detailed schedule.



10/05 – 11/07

3/26 – 10/03

1/12 – 3/25

* *http://filebox.vt.edu/users/alanma/bit3434/pm2chart.JPG*

The preliminary budget and resources can be seen below:

|  |  |  |
| --- | --- | --- |
| **Item** | **Cost** | **Rationale** |
| Microsoft Project | License Fee | Primary Tool for Communication |
| Meeting Rooms | NA | Team Meetings |
| Tables, Views, and Reports | Internal Team Time | End Product Development |
| Team Member Hours | 200 Team Hours | Primary Work of Project |

Overall expectations include: the project will include iterations, reporting development will require collaboration between the five stakeholders, and as the project develops additional resources will be allocated to fulfill needs. Assumptions include mutual buy-in from the stakeholders, flexibility in the reporting requirements, and mutual benefit to MMBI as the report becomes available. Given the data breach during the holiday season, impact reporting will be purposely excluded.

Project organization includes: Dan Prusinski – project manager, James Nelson – project funder, Jacob Yunker – guest data coordinator, Alex Miller – implementation coordinator, Ryan Ruffcorn – reporting coordinator, Carl Cooley – division insights coordinator, Jarrett Reed – DIL coordinator. The responsibility matrix can be seen below:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Task | James | Dan | Alex | Jacob | Carl | Ryan | Jarrett |
| Identify Target Guest Metrics for Reporting | R | S |  | S | S |  | S |
| Develop Report Template |  | S |  |  |  | R |  |
| Pilot Report |  | R |  |  |  | S |  |
| Create re-occurring reporting schedule |  | S |  |  |  | R |  |
| Present Reporting Tool |  | R | S |  |  |  |  |
| Create Predictive Models based on Report | S | R |  | S | S |  |  |
| Present Key Findings to Management | R | S |  |  |  |  | S |
| Provide Documentation for Iterations | S | R | S |  |  |  |  |
| Responsible = R |
| Support = S |

At this point in project MetaGuest, management is working closely with the project manager to develop and scope the overall plan. Iterations are expected to sharply shape the project planning in the next two weeks.

Process Breakdown Structure for project MetaGuest

Test Phase Deliverables:

Test Document

Manager Testing Feedback

User Feedback

Coding Iterations SQL

Coding Iterations IR

Rollout Phase Deliverables:

Physical/Electronic PowerPoint

Pre-Code Embedded in PP

Document

Feedback from Users

Iterate in SQL

Construct Phase Deliverables:

SAS Code Written

Teradata Code Written

Hadoop Code Written

Design Phase Deliverables:

MicroStrategy View

Tableau View

ADW Data Repository

EDW Data Repository

Analysis Phase Deliverables:

Analysis Document

RFV Breakdown

Lifestage Analysis

Guest Trip Segmentation

Guest Spend Segmentation

Stable Guest Logic Interval

Outputs:

1.5.2.2

1.5.2.1

1.5.1.2

1.5.1.1

1.5.2

1.5.1

Record

Wrap Up

Demonstration

PowerPoint

Feedback

Presentation

1.5

Rollout

1.4.2.2

1.4.2.1

1.4**.**1.2

1.4**.**1.1

IR

SQL

Users

Manager

1.4.2

1.4**.**1

Iterations

1.4

1.4

Group

Test

1.3.3

1.3.2

1.3.1

Hadoop

Teradata

SAS

1.3

Construct

1.2.2.2

1.2.2.1

EDW

ADW

1.2.1.2

1.2.1.1

Tableau

MicroStrategy

1.2.2

Repository

1.2.1

Template Views

1.1.2.1

Stable Guest Logic

1.1.2

Guest Spend

1.1.1.3.2

1.1.1.3.1

1.1.1.3

1.1.1.2

1.1.1.1

Guest Trips

Guests

Lifestage

RFV

1.1.1

Establish Time Interval

Define Key Metrics

1.5

1.3

1.2

1.1

Analysis

Design

Construct

Test

Rollout

1.0

MetaGuest Development Project

Analysis


1.0

1.0

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **Time-Cost Labor Estimates** | | | | | | | |
| **WBS ID** | **Task Description** | **Estimate (hrs)** | **Estimating Approach** | **Estimated Duration (hrs)** | **Estimated Interruptions (hrs)** | **Total Duration (hrs)** | **Labor Rate $/hr** | **Labor Cost Total $** |
| 1.0 | MetaGuest Project | 200 | Bottom Up (BU) | 264.0 | 64.0 | 328.0 | 50, 65, 75, 150 | $ 24,200 |
|  |  |  |  |  |  |  |  |  |
| 1.1 | Analysis | 6 | BU Template | 6.0 | 2.0 | 8.0 | $65 | $ 520 |
|  |  |  |  |  |  |  |  |  |
| 1.1.1 | Define Metrics (Calculate) | 4 | BU Template | 4.0 | 4.0 | 8.0 | $65 | $ 520 |
| 1.1.1.1 | RFV (Compile) | 5 | BU Template | 5.0 | 1.0 | 6.0 | $50 | $ 300 |
| 1.1.1.2 | Lifestage (Build) | 5 | BU Template | 5.0 | 1.0 | 6.0 | $50 | $ 300 |
| 1.1.1.3 | Guests (Assemble) | 10 | BU Template | 10.0 | 2.0 | 12.0 | $75 | $ 900 |
| 1.1.1.3.1 | Guest Trips (Calculate) | 6 | BU Template | 6.0 | 2.0 | 8.0 | $75 | $ 600 |
| 1.1.1.3.2 | Guest Spend (Compile) | 4 | BU Template | 4.0 | - | 4.0 | $75 | $ 300 |
|  |  |  |  |  |  |  |  | $ - |
| 1.1.2 | Establish Time (Compile) | 2 | BU Template | 2.0 | - | 2.0 | $65 | $ 130 |
| 1.1.2.1 | Guest Logic (Calculate) | 8 | BU Template | 8.0 | 2.0 | 10.0 | $75 | $ 750 |
|  |  |  |  |  |  | - |  | $ - |
| 1.2 | Design (Compile) | 6 | BU Template | 6.0 | 2.0 | 8.0 | $65 | $ 520 |
| 1.2.1 | Template Views (Build) | 2 | BU Template | 2.0 | - | 2.0 | $65 | $ 130 |
| 1.2.1.1 | Microstrategy (Build) | 4 | BU Template | 4.0 | - | 4.0 | $50 | $ 200 |
| 1.2.1.2 | Tableau (Build) | 6 | BU Template | 6.0 | 1.0 | 7.0 | $75 | $ 525 |
|  |  |  | BU Template |  |  | - |  | $ - |
| 1.2.2 | Repository (Document) |  | BU Template |  |  | - |  | $ - |
| 1.2.2.1 | ADW (Build) | 8 | BU Template | 8.0 | 2.0 | 10.0 | $75 | $ 750 |
| 1.2.2.2 | EDW (Build) | 8 | BU Template | 8.0 | 2.0 | 10.0 | $75 | $ 750 |
|  |  |  |  |  |  | - |  | $ - |
| 1.3 | Construct (Document) | 6 | BU Template | 6.0 | 1.0 | 7.0 | $65 | $ 455 |
| 1.3.1 | SAS (Coding) | 4 | BU Template | 4.0 | - | 4.0 | $75 | $ 300 |
| 1.3.2 | Teradata (Coding) | 6 | BU Template | 6.0 | 1.0 | 7.0 | $75 | $ 525 |
| 1.3.3 | Hadoop (Coding) | 8 | BU Template | 8.0 | 2.0 | 10.0 | $75 | $ 750 |
|  |  |  |  |  |  | - |  | $ - |
| 1.4 | Test (Document) | 4 | BU Template | 4.0 | - | 4.0 | $65 | $ 260 |
| 1.4.1 | Group (Compile) | 2 | BU Template | 2.0 | - | 2.0 | $65 | $ 130 |
| 1.4.1.1 | Manager (Trial) | 8 | BU Template | 16.0 | 4.0 | 20.0 | $150 | $ 3,000 |
| 1.4.1.2 | Users (Trial) | 8 | BU Template | 24.0 | 8.0 | 32.0 | $65 | $ 2,080 |
|  |  |  |  |  |  | - |  | $ - |
| 1.4.2 | Iterations (Document) | 10 | BU Template | 20.0 | 8.0 | 28.0 | $65 | $ 1,820 |
| 1.4.2.1 | SQL (Coding) | 12 | BU Template | 24.0 | 6.0 | 30.0 | $75 | $ 2,250 |
| 1.4.2.2 | IR (Coding) | 12 | BU Template | 24.0 | 6.0 | 30.0 | $75 | $ 2,250 |
|  |  |  |  |  |  | - |  | $ - |
| 1.5 | Rollout (Document) | 4 | BU Template | 6.0 | 1.0 | 7.0 | $65 | $ 455 |
| 1.5.1 | Presentation (Build) | 8 | BU Template | 8.0 | 2.0 | 10.0 | $65 | $ 650 |
| 1.5.1.1 | PowerPoint (Compile) | 4 | BU Template | 4.0 | - | 4.0 | $65 | $ 260 |
| 1.5.1.2 | Demonstration (In Person) | 6 | BU Template | 8.0 | 2.0 | 10.0 | $65 | $ 650 |
|  |  |  |  |  |  | - |  | $ - |
| 1.5.2 | Feedback (Document) | 4 | BU Template | 4.0 | - | 4.0 | $65 | $ 260 |
| 1.5.2.1 | Record (Compile) | 6 | BU Template | 8.0 | 2.0 | 10.0 | $65 | $ 650 |
| 1.5.2.2 | Iterate (In Person) | 4 | BU Template | 4.0 | - | 4.0 | $65 | $ 260 |
|  |  |  |  |  |  | - |  | $ - |
|  |  |  |  |  |  | - |  | $ - |
|  | **Top Down Estimation** | | | | | | | |
| 1.3 | Construct (Document) | 2 | Consensus | 2.0 | - | 2.0 | $65 | $ 130 |
| 1.3.1 | SAS (Coding) | 4 | Consensus | 4.0 | - | 4.0 | $75 | $ 300 |
| 1.3.2 | Teradata (Coding) | 4 | Consensus | 4.0 | - | 4.0 | $75 | $ 300 |
| 1.3.3 | Hadoop (Coding) | 4 | Consensus | 6.0 | 1.0 | 7.0 | $75 | $ 525 |
|  | Total | 14 |  | 16 | 1 | 17 |  | $ 1,255 |

Target’s Business Intelligence has been building reports for over five years. MetaGuest has similar components to past projects based on the overall objective of creating a report. The analysis, coding, design, testing, and rollout aspects of the project have prior templates. The difference in this report is that the metrics being reported on are newly developed in addition to the Hadoop software interface. From researching in *Project Management* (Larson & Gray), the Template Method of Bottom-Up Approaches is the best suited method for estimation with MetaGuest. Given that many of the processes in the project have past information and templates, it is logical and efficient to use this estimation method.

In an effort to explore an additional estimation method, I used the Top-Down approach and the Consensus method. This project is small enough that the Delphi Method is not necessary. In my opinion, management shortchanged the project package. The issue is most evident in the Teradata and Hadoop coding aspects. Management is applying the same number of hours for all three coding languages. The issue is that Teradata and Hadoop are brand new languages to Target and the systems do not run as smoothly as SAS. The shortcoming is that management is not aware of this nuance and shortchanged this process.



|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **MetaGuest Activity Order** | | | | |
| **Activity** | **WBS Code** | **Hours** | **Description** | **Preceding** |
| A | 1.1.1.1 | 5 | Establish Guest RFV Breakdown from Demo Table Data | None |
| B | 1.1.1.2 | 5 | Establish Lifestage Breakdown from Guest Table | None |
| C | 1.1.1.3 | 10 | Guest Trips and Spend from Transaction Table (Very Similar Table) | None |
| D | 1.1.2  1.1.2.1 | 10 | Trend Stable Guest Logic for Weekly Interval | None |
| E | 1.1  1.1.1 | 10 | Document Key Metrics for MetaGuest as Best Practice (Milestone) | A,B,C,D |
| F | 1.2.1.1 | 4 | Design MicroStrategy Dashboard using Key Metrics | E |
| G | 1.2.1.2 | 6 | Design Tableau Dashboard using Key Metrics | E |
| H | 1.2  1.2.1 | 8 | Document Dashboard Code in Best Practice Format | F,G |
| I | 1.2.2.1 | 8 | Establish connection/network for Analytical Data Warehouse | H |
| J | 1.2.2.2 | 8 | Establish connection/network for Enterprise Data Warehouse | H |
| K | 1.2.2 | 6 | Document Data Warehousing Code in Best Practice Format | I,J |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **MetaGuest Activity Order** | | | | |
| **Activity** | **WBS Code** | **Hours** | **Description** | **Preceding** |
| L | 1.3.1 | 4 | Write SAS code for Dashboard/Key Metrics | K |
| M | 1.3.2 | 6 | Write Teradata code for Dashboard/Key Metrics | K |
| N | 1.3.3 | 8 | Write Hadoop code for Dashboard/Key Metrics | K |
| O | 1.3 | 6 | Back Interpret All Aspects of SAS, Teradata, Hadoop | L,M,N |
| P | 1.4.1.1 | 8 | Demonstrate/Explain Initial Report for Management | O |
| Q | 1.4.1.2 | 8 | Pilot Initial Report with Specific Users | P |
| R | 1.4  1.4.1 | 6 | Document Findings from Management and Users | Q |
| S | 1.4.2.1 | 12 | Make Iterations to Overall Project Utilizing SQL Language | R |
| T | 1.4.2.2 | 12 | Make Iterations to Overall Project Utilizing IR Language | R |
| U | 1.4.2 | 10 | Make Iterations Known to Management and Users | S,T |
| V | 1.5.1.1 | 4 | Create PowerPoint for Official Rollout Presentation | U |
| W | 1.5.1 | 8 | Create Demonstration and Integrate into PowerPoint | V |
| X | 1.5.1.2 | 4 | Run Presentation with Management and Users | W |
| Y | 1.5.1.2 | 2 | Collect Feedback from Management and Users | X |
| Z | 1.5 | 4 | Wrap-up All Aspect of Project into Electronic and Physical Copies | Y |

Risk Breakdown Structure

**RISK ASSESSMENT MATRIX**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Risk Event** | **Likelihood** | **Impact** | **Detection Difficulty** | **When** |
| Server Space | 4 | 3 | 2 | Start-Up, Rollout |
| MicroStrat Crash | 4 | 2 | 5 | Design |
| Programmer Quitting | 3 | 3 | 3 | Construct, Test, Rollout |
| IR Failure (Hardware) | 1 | 5 | 5 | Testing |
| User Backlash | 3 | 4 | 2 | Rollout |

Red zone (major risk)

Yellow zone (moderate risk)

Green zone (minor risk)

Likelihood

Impact



**RISK RESPONSE MATRIX**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Risk Event** | **Response** | **Contingency**  **Plan** | **Trigger** | **Responsible**  **Party** |
| Server Space | Change data dump locations, contact TTS immediately | Upload initial design to Target Cloud Space | Exceed initial capacity | James Nelson with the Support of Daniel Prusinski |
| MicroStrat Crash | Submit tick to TTS | Run code through SAS environment | Too many reports running on system | Ryan Ruffcorn  Dan Ryks |
| Programmer Quitting | Alert director | Have two contractors briefed. | Lack of communication and unknown | Daniel Prusinski  Colleen Theisen |
| IR Failure (Hardware) | Transfer code to new hardware | Back up all code on externally | Hardware fails | Mark VonOven |

Yes

No

Programmer Quits

Project Change Form (PCM) Emailed to PM

PM Reviews PCM

Communication Understood ? Email Team

Call in Contractor

Onboard New Hire

Introduce to Team and Establish Responsibilities

Remove Contractor from Programming ilities

MetaGuest Change Form

Requestor Name: ­Kyle Kruegger Date: 2/6/2014 Request #:\_\_\_1\_\_\_

Type of Request: Please put in Subject line of email along with Change Form:

Urgent Moderate Low Impact

Change Requested by/Date: 2/18/2014

Description of Requested Change: \_\_\_\_\_Robert has decided to pursue opportunities elsewhere, I will begin the hiring process on Monday.

Reason for Change:\_Better commuting for his family. \_\_\_\_

Area of impact on project for proposed change (Please circle one or more)

Analysis Design Construct Test Rollout Other:\_\_\_\_\_\_\_\_\_\_\_

Disposition

\_\_Approve \_X\_Approve as Amended \_\_Disapproved

Comments:

\_\_\_\_\_\_\_\_\_Lets’ talk on Monday about who we want to hire.\_\_\_\_\_\_\_\_\_\_\_\_\_

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Funding Source

\_\_Customer \_X\_Sponsor \_\_Other:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Sign-off

Project Manager:\_\_\_\_DSP\_\_\_\_\_\_\_\_\_\_

Project Customer:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Human Resources Management Plan

Roles and Responsibilities:

Project MetaGuest is a completely internal project that will follow suit within Target’s matrix structure organization. The following staffing requirements are necessary for completing MetaGuest within the stringent timeline:

Project Manager (1 Position) – The project manager is ultimately responsible for all aspects of managing the project, overall administration duties, and communication of results and iterations. Authority is linked through submittal of a performance review for all project team members and will have direct correlation with annual raises, terminations, or performance improvement plans. The ideal candidate will have prior 1 year prior project management experience, knowledge of data housing and manipulation software, and familiarity with data reporting structure at Target.

Data Analyst (4 Positions) – The data analyst is responsible for establishing key metrics for the new reporting techniques. The four different positions will require specific subject matter expertise in: RFV delineation, Lifestage calculation, Trip Spend definition, Stable Time Logic acquisition. This is an individual contributor role without any authority beyond project contribution. Upon completion of the project, the project manager will evaluate your contribution and it will be reviewed as the annual innovation project in the annual review. The ideal candidate will have active knowledge of specific subject matter, demonstrated time management skills as well as deadline delivery success, and permission from manager.

Senior Analyst (1 Position) – The senior analyst will interpret and document all coding aspects of project MetaGuest. This position works in close tandem with the project manager and is preceding experience for project management roles. All analysts and programmers report to the senior analyst. Incentive is being offered based on ratings from direct reports. The ideal candidate will have excellent communication skills both written and verbal. Coding languages including: SAS, SQL, Teradata, Tableau, Hadoop, and IR are necessary for this role. This is an entry level leadership role with the ideal candidate being endorsed as a leader from their manager.

Programmer (9 Positions) – A programmer from the following languages is needed: MicroStrat, Tableau, ADW, EDW, SAS, TeraData, Hadoop, SQL, and IR. The programmer will write basic reporting code that complies with Target’s best practices with subtext for basic documentation. As an individual contributor you will be responsible for your work and the joining acquisition found in the AON. Direction is supported through the senior analyst. MetaGuest is within the Innovation project strategy and will be documented in the programmers annual review. The ideal candidate will be comfortable working on a collaborative meeting for a short time, proven coding track record, and excellent communication skills.

MetaGuest Organization Chart

Staff Management Plan

Staff Acquisition: Given the matrix structure of Target, this project will follow suit. This project falls within the overall Innovation project space, of which all departments contribute towards. The positions will be communicated from the director to the mangers, and sent out via email through the project promotion channel. The resource calendar along with the time phased budge can be found in appendix 2 and 3. Resources are based on hourly completion and must be followed within the order detailed in appendix 2. Given the detailed, disparate, and relatively short nature of the programming and analysis positions, roles are subject to one contributor rather than adding additional resources. Applications are open until filled and manager consent is necessary for all analyst/programmer roles with a signature required for understanding the resource calendar, which will serve as the release notice. Given the high nature of the roles for this project, it is expected that team members will balance the project with their other assigned responsibilities. There is not additional training needed for this project. Recognition and rewards will be communicated to mangers as well as the annual performance review. Compliance and safety is within the parameters of the general work contracts of all participants.

Schedule Management Plan

The full project schedules can be found in appendix 2 and 3. Given that this project is internal, time constraint is more of a focus rather than resource. Project MetaGuest falls within the corporate initiative as an Innovation Project and is allotted 20% of team member’s time per day. The resource schedule shows a detailed breakdown based on hourly resource use. Building on the resource schedule, the hours role up into days and days role up into weeks, which can be seen on the Schedule Model Development chart. The level of accuracy is estimated down to the hour, which is the core unit measure for this project.

MetaGuest requires nine different coding languages, which requires nine different programmers. In addition, the coding responsibilities are rather short in comparison to coding norms, the two mentioned nuances inhibit any resource leveling to utilize the project little project slack.

Organizational procedures links MetaGuest to Target in the following diagram.

Innovation Goals: Analytics

Ceo: 2014

Roadmap

Innovation

Projects

Project MetaGuest

BI&A

(Analysts) 

Data Quality (EDW)

Individuals within the departments submit applications to work on Project MetaGuest

Data Quality (ADW)

BI&A

(Analysts) 

BI&A

(Programmers) 

Once the project is approved, positions will be posted and filled in the following order. Project Manager, Senior Analyst, Analyst, and Programmer. The project schedule model maintenance can best be described through the following diagram:

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **WBS Code** | **Hours** | **Description** |
| A | 1.1.1.1 | 5 | Establish Guest RFV Breakdown from Demo Table Data |

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **WBS Code** | **Hours** | **Description** |
| B | 1.1.1.2 | 5 | Establish Lifestage Breakdown from Guest Table |

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **WBS Code** | **Hours** | **Description** |
| E | 1.1  1.1.1 | 10 | Document Key Metrics for MetaGuest as Best Practice (Milestone) |

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **WBS Code** | **Hours** | **Description** |
| C | 1.1.1.3 | 10 | Guest Trips and Spend from Transaction Table (Very Similar Table) |


|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **WBS Code** | **Hours** | **Description** |
| D | 1.1.2  1.1.2.1 | 10 | Trend Stable Guest Logic for Weekly Interval |

MetaGuest has 6 activities similar to Activity E where code is documented and thoroughly analyzed. These activities are planned with the intention of being the main point for project maintenance and a gut check for overall progress. Within these activities changes are most likely to be made, and the project change form will be used. The similar activities are: E, H, K, O, R, and U. Each of these activities also serve as a project milestone.

Control thresholds are within Target’s general operation thresholds, and requires no further documentation. Performance measurements are primarily subjected to documentation standards and efficient code running. At each milestone, the senior analyst will communicate with programmers and analysts if the basic coding is not up to standard. Reporting formats will be in basic Target best practices documentation as seen below:

Appendix 2:


Resource and Time Schedule




|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID | | | Resources | | | | | | | | | | | | | | H | | | | O | | | | U | | | | R | | | S | | |  | | |  | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | | |  |
| A | | | 1 | | | | Analyst | | | | | | | | | | 1 | | | | 1 | | | | 1 | | | | 1 | | | 1 | | |  | | |  | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | | |  |
| B | | | 1 | | | | Analyst | | | | | | | | | | 1 | | | | 1 | | | | 1 | | | | 1 | | | 1 | | |  | | |  | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | | |  |
| C | | | 1 | | | | Analyst | | | | | | | | | | 1 | | | | 1 | | | | 1 | | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | | 1 | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | | |  |
| D | | | 1 | | | | Analyst | | | | | | | | | | 1 | | | | 1 | | | | 1 | | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | | 1 | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | | |  |
| E | | | 1 | | | | Senior Analyst | | | | | | | | | |  | | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | | 1 | | | 1 | | | | 1 | | | 1 | | | 1 | | |  | | |  | | |  | | |  | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | | |  |
| F | | | 1 | | | | Programmer | | | | | | | | | |  | | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | | |  | | |  | | |  | | | 1 | | | 1 | | | 1 | | | 1 | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | | |  |
| G | | | 1 | | | | Programmer | | | | | | | | | |  | | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | | |  | | |  | | |  | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | | 1 | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | | |  |
| H | | | 1 | | | | Senior Analyst | | | | | | | | | |  | | | |  | | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | |  | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | |  | | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | | |  |
| 1 | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | 1 | | | | I | | | 1 | | | Programmer | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |
| 1 | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | 1 | | | | J | | | 1 | | | Programmer | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |
|  | |  | | |  | | |  | | |  | | |  | |  | | | | 1 | | | 1 | | | 1 | | 1 | | | 1 | | | 1 | | | K | | | 1 | | | Senior Analyst | | | | | | | | | | | | | | | | | | | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |
| L | | 1 | | | Programmer | | | | | | | | | | | | | | | | | |  | | |  | |  | | |  | | |  | | | 1 | | | 1 | | | 1 | | | 1 | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |
| M | | 1 | | | Programmer | | | | | | | | | | | | | | | | | |  | | |  | |  | | |  | | |  | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |
| N | | 1 | | | Programmer | | | | | | | | | | | | | | | | | |  | | |  | |  | | |  | | |  | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |
| O | | 1 | | | Senior Analyst | | | | | | | | | | | | | | | | | | | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | 1 | | | 1 | | 1 | | | 1 | | | 1 | | | 1 | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |
| P | | 1 | | | Project Manager | | | | | | | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | 1 | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |
| Q | | 1 | | | Project Manager | | | | | | | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | |  | |  | | |
| R | | 1 | | | Project Manager | | | | | | | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | 1 | | 1 | | |
|  | | | |  | | | | |  | | |  | 1 | | 1 | | | | 1 | | | 1 | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | S | | | 1 | | | Programmer | | | | | | | | | | | | | | | | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | |
|  | | | |  | | | | |  | | |  | 1 | | 1 | | | | 1 | | | 1 | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | T | | | 1 | | | Programmer | | | | | | | | | | | | | | | | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | |
| U | | | | 1 | | | | | Project Manager | | | | | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | 1 | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | |
| V | | | | 1 | | | | | Project Manager | | | | | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | | 1 | | | 1 | | | 1 | | | 1 | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | |
| W | | | | 1 | | | | | Project Manager | | | | | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | | 1 | | | 1 | | | 1 | | | 1 | | | 1 | | 1 | | | 1 | | | 1 | | |  | | |  | | |  | | |  | | |  | | |  | |  | |
| X | | | | 1 | | | | | Project Manager | | | | | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | | 1 | | | 1 | | | 1 | | | 1 | | |  | | |  | |  | |
| Y | | | | 1 | | | | | Project Manager | | | | | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | | 1 | | | 1 | |  | |
| Z | | | | 1 | | | | | Project Manager | | | | | | | | | | | | | | | | | | | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | |  | | 1 | |
| 1 | 1 | | | | | 1 | | | | 5 | | | | | | | |

Appendix 3

Time Schedule Breakdown



|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |



Appendix 3: Leadership and Project Management Experiences

Through my young career, I have had the amazing opportunity to work for exceptional leaders, project managers (PMs), as well as PMs in a leadership capacity. Jointly, there have been instances with the above positions where experiences were soured as a result of failed performance.

In my past position, I worked in refugee resettlement and my supervisor was responsible for the global operations for the organizations. On multiple occasions, I had other companies offer me positions, often making more than 50% more of what I was being paid. The main reason why I remained in my position was my supervisor was an amazing leader. In his previous role in the banking industry as an executive, he led over 200 individuals and managed the underlying responsibility.

During our first one on one meeting, he truly inspired me through the following experience. This is how the first conversation went (Verbatim) “Hi Dan, it’s nice to meet you, I’ve heard you have been doing some great work around here. I am hoping that in our first meeting you can help me better understand where I can help the projects you are currently working on, where you might need resources that I can help you get, and finally share with me areas where I should stay out of your way (Richard Payne).” I was truly blown away from this first interaction, and walking away from that meeting I felt that my boss was for me. He most exemplified servant/transformational leadership theory. Richard understood my driver personality, how to motivate me beyond the position, and inspire me to grow as one of his subordinates. He took the time before the meeting to research my work and understand how best to motivate me. In the long run, this set him up for success because through his demonstration of servant leadership I became inspired to perform, win for the department, and make him look good. Our team was very effective under Richard’s leadership because he led by example and his leadership style acquiesced very well with everyone on the team.

As I take on more leadership roles, I strive to put into action the three main points Richard asked me. Tell me about your work, how can I help, how can I stay out of the way? As I work with people, this communicates that the leader cares, seeks to positively transform the individual, and recognize the need to stay out of certain projects (this build trust). These are rather simple concepts, but I greatly desire to put them into practice as I move forward in leadership.

While in my refugee resettlement role, I observed another leaders interaction. In many instances, this leader failed to enforce a model work ethic through little time in the office or MBWA. Furthermore, he failed to inspire his team as well as convey that he cared about their work. On a personal level, this individual was very friendly, smart, and easy to converse with. As a leader, his failure to inspire, convey genuine interest, and demonstrate work ethic resulted in two of his subordinates quitting as well as his administrative assistant.

The takeaways from the above situation are simple yet profound. Leaders need to demonstrate they are hard workers, simply put. I saw firsthand how morale is linked to the demonstration of a work ethic. Second, taking genuine interest in someone’s work goes beyond asking the question, “what are you working on?” One needs to act engaged and seek to further another’s work. Third, inspiration is not easily executed. It takes intention, apt delivery, and sincerity. I don’t doubt that the failed leader sincerely wanted his subordinates to succeed, but he failed to inspire his team.

As I develop my leadership skills, I will hone in on demonstrating a solid perception of work ethic, inspiration, and sincerity. These attributes are not easily executed, but I have a deep passion to develop.

Alaska is a beautiful state, and I had the opportunity to work as a project manager on construction project. The primary client was an Athabascan Chief, and we were building a Retreat Center on his land. Mid-way through the project funding was greatly reduced due to the Great Recession. The Sr. Project Manager (SPM) had known for months that the project was ill funded but failed to communicate the change until two weeks before major construction was to start on the main facility. This created ill-will and a feeling of distrust between the clients and our construction teams. Work massively slowed, relationships were unnecessarily strained, and productivity suffered. The major failings were the lack of communication and failure to manage expectations. Setbacks are inevitable, but the SPM gravely misunderstood the clients need for continual communication about finances and not just the project’s wins. I have learned from this scenario to manage key relationships with great intent, and no news if often bad news. Part of managing a relationship is being candid, I understand it is important to win over clients, but honesty with tactfulness sustains a relationship. As a result of the SPM lack of communication and management, the entire team had great difficulty implementing the rest of the project.

Chapter 15 of Project Management discusses international projects and culture. When I was in Afghanistan, I had the opportunity to experience my Project Manager navigate Afghan politics exceptionally well. He would meet with provincial governors, mayors, and heads of state but purposely kept at arms distance. Corruption was rampant by USAID standards and he maintained social acumen without getting caught up in the politics. He maintained a position of honoring those in authority without being called upon for “favors”. Our team learned the value of managing relationships from a safe distance. As a result of the PMs shrewd cultural navigation, out team had top talent and remained focused on the task at hand as opposed to loosing focus and energy on matters not relevant to our project. I have applied this to my working relationships in that when managing projects I purposely avoid conversations and places where I might lose focus.

One of my major first projects in refugee resettlement was to host a huge dinner for Somali dignitaries, government officials, and local refugees. My manager was the acting senior project manager (SPM) and one of the key honored guests. When the night of the big dinner was in full swing, we had a huge turnout. As the event progressed, my SPM jumped in the front lines of the evening by taking out trash cans, serving food to the refugees, and cleaning up mild spills. I was taken back by and inspired by his hands-on approach, there was no task too low that he would not take on. Walking away from that project, the team and I learned that if our SPM would serve a project in the capacity he demonstrated that night, we too would have to emulate that same attitude and behavior. The bar was raised after that night, and the team grew in maturity from the sense that we all new that the buck stopped with us and we were inspired to take on any task to fruition for the sake of a successful project. Since that night, in my new company and role if we are entering a meeting and someone is setting up I will jump in and assist in the setup. I do whatever it takes to assist in completion of remedial tasks despite who is or isn’t looking. The overall theme I have applied is despite years of work and titles, there is no role that a project manager should participate in that is too low.

My project manager in Afghanistan did a great navigating the political landscape of Afghanistan, but he had trouble leading the local Afghans on our team. Issac was Ugandan, and in his culture they value direct communication and being blunt. Afghanistan is more of an Asian culture in that shame is never directly imposed on individuals. The danger in applying shame came have very negative consequences. Issac on multiple occasions would castigate locals Afghans and other team members in front of other Afghans and team members. This resulted in massive amounts of shame being imposed on individuals. As a result of his cultural insensitivity, one of our team members threatened to blow up our compound and he was fired. In addition, the Afghan nationals would avoid and lie to Isaac because of his confrontational management style. There was a great deal of dysfunction and our team failed to bond. I have learned that when correcting and reprimanding individuals to do it in private (most situations), and have an attitude of restoration not confrontation. This has helped me to preserve relationships while still being candid.

Book Subjects

• Executive Summary - pg. 516  
• Project Scope Statement - pgs. 102 - 106  
• Priority Matrix - Fig 4.2  
• Stakeholder Register - template in Course Content  
• Work Breakdown Structure - pgs. 108 – 116 Fig 4.5  
• Gantt chart (Baseline) - Fig 13.1  
• AON Network Diagram Fig 6.8  
• Project Baseline Budget - Fig 8-16  
• Communications Plan – pgs 118 – 122  
• Risk Assessment Matrix - Fig 7.6  
• Risk Response Matrix - Fig 7-8  
• Project Organization - various Chap 3, Fig 3.3  
• Feasibility - answer the question, Is this project viable and what makes you think so?  
• Integration - pgs. 11-23, 68, 70, 73