## Sheet1
ID | Duration | Task | Budget (Hours) | Weeks
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | Week 1 | 30
A | 5 | Establish Guest RFV | 5 | Weeks 1: 5; Weeks Week 1: Week 2; Weeks 30: 40
B | 5 | Establish Lifestage | 5 | Weeks 1: 5; Weeks Week 1: Week 3; Weeks 30: 54
C | 10 | Guest Trips and Spend | 10 | Weeks 1: 10; Weeks Week 1: Week 4; Weeks 30: 70
D | 10 | Trend Stable Guest Logic | 10 | Weeks 1: 10; Weeks Week 1: Week 5; Weeks 30: 86
E | 10 | Document Key Metrics | 10 | Weeks 2: 10; Weeks Week 1: Week 6; Weeks 30: 102
F | 4 | Design MicroStrategy | 4 | Weeks 3: 4; Weeks Week 1: Week 7; Weeks 30: 112
G | 6 | Design Tableau | 6 | Weeks 3: 6; Weeks Week 1: Week 8; Weeks 30: 122
H | 8 | Document Dashboard | 8 | Weeks 3: 4; Weeks 4: 4; Weeks Week 1: Week 9; Weeks 30: 138
I | 8 | Establish ADW | 8 | Weeks 4: 6; Weeks 5: 2; Weeks Week 1: Week 10; Weeks 30: 154
J | 8 | Establish EDW | 8 | Weeks 4: 6; Weeks 5: 2; Weeks Week 1: Week 11; Weeks 30: 164
K | 6 | Document Data | 6 | Weeks 5: 6; Weeks Week 1: Week 12; Weeks 30: 174
L | 4 | Write SAS code | 4 | Weeks 5: 2; Weeks 6: 2; Weeks Week 1: Week 13; Weeks 30: 182
M | 6 | Write Teradata code | 6 | Weeks 5: 2; Weeks 6: 4
N | 8 | Write Hadoop code | 8 | Weeks 5: 2; Weeks 6: 6
O | 6 | Back Interpret | 6 | Weeks 6: 4; Weeks 7: 2
P | 8 | Report for Management | 8 | Weeks 7: 8
Q | 8 | Pilot | 8 | Weeks 8: 8
R | 6 | Document Findings | 6 | Weeks 8: 2; Weeks 9: 4
S | 12 | Make SQL Iterations | 12 | Weeks 9: 6; Weeks 10: 6
T | 12 | Make IR Iterations | 12 | Weeks 9: 6; Weeks 10: 6
U | 10 | Showcase Changes | 10 | Weeks 10: 4; Weeks 11: 6
V | 4 | Create PowerPoint | 4 | Weeks 11: 4
W | 8 | Create Demonstration | 8 | Weeks 12: 8
X | 4 | Run Presentation | 4 | Weeks 12: 2; Weeks 13: 2
Y | 2 | Collect Feedback | 2 | Weeks 13: 2
Z | 4 | Wrap-up | 4 | Weeks 13: 4
Total | 182 | Week Total (Hours) |  | 30 | 10 | 14 | 16 | 16 | 16 | 10 | 10 | 16 | 16 | 10 | 10 | 8
|  | Running Total (Hours) |  | 30 | 40 | 54 | 70 | 86 | 102 | 112 | 122 | 138 | 154 | 164 | 174 | 182