## Sheet1
Cost Variance |  | CV=EV - AC
Schedule Variance |  | SV = EV - PV
Status Report: Ending Period One
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
A | 100% | 5 | 5 | 5 | 0 | 0 | 1 | 1
B | 100% | 5 | 5 | 5 | 0 | 0 | 1 | 1
C | 100% | 10 | 10 | 10 | 0 | 0 | 1 | 1
D | 100% | 10 | 10 | 10 | 0 | 0 | 1 | 1
Cumulative Total |  | 30 | 30 | 30 | 0 | 0 | 1 | 1
Notes: Analysts finished work on time and looking forward to back documentation.
Status Report: Ending Period One
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
E | 100% | 10 | 10 | 10 | 0 | 0 | 1 | 1
Cumulative Total |  | 10 | 10 | 10 | 0 | 0 | 1 | 1
Notes: Back documentation is set in place and project is ready for dashboard design.
Step 1. You should develop the baseline for the entire project (see Fig 13.8), should be the cost baseline from Session 6.
Step 2. You can pick a time period approximately 1/3 the way through the project. If your project is highly complicated, you might pick a shorter period of time; we just need a planned number to compare to.
Step 3. You can introduce some problems that cause your project to be behind. Don't spend a great deal of time on developing this. Just create some delays or even some advances that change those actual costs.
Step 4. Then calculate the SV, CV, SPI, & CPI for the project at that point in time. See pages 463-472. Show it in a table like Table 13.2 on page 470.
Step 5: Write a brief status report, 2-3 paragraphs, explaining the various EVA indices and variances and what they tell you about the status of the project at that time.