## Sheet1
Cost Variance |  | CV=EV - AC
Schedule Variance |  | SV = EV - PV
Status Report: Ending Period One
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
A | 100% | 500 | 500 | 500 | 0 | 0 | 1 | 1
B | 100% | 500 | 500 | 500 | 0 | 0 | 1 | 1
C | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
D | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
Cumulative Total |  | 3000 | 3000 | 3000 | 0 | 0 | 1 | 1
Notes: Analysts finished work on time and looking forward to back documentation.
Status Report: Ending Period Two
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
A | 100% | 500 | 500 | 500 | 0 | 0 | 1 | 1
B | 100% | 500 | 500 | 500 | 0 | 0 | 1 | 1 |  |  | Step 5: Write a brief status report, 2-3 paragraphs, explaining the various EVA indices and variances and what they tell you about the status of the project at that time.
C | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
D | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
E | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
Cumulative Total |  | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
Notes: Back documentation is set in place and project is ready for dashboard design.
Status Report: Ending Period Three
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI | CPI% | SPI%
A | 100% | 500 | 500 | 500 | 0 | 0 | 1 | 1
B | 100% | 500 | 500 | 500 | 0 | 0 | 1 | 1
C | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
D | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
E | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
F | 80% | 320 | 500 | 400 | -180 | -80 | 0.64 | 0.8
G | 100% | 600 | 600 | 600 | 0 | 0 | 1 | 1
H | 100% | 400 | 400 | 400 | 0 | 0 | 1 | 1
Cumulative Total |  | 4320 | 5500 | 5000 | -180 | -80 | 0.94857 | 0.97143 | 5.143% | 2.857%
Notes: The design for MicroStrategy has taken longer than expected
based on server connection issues. Please note that back documenting
is still on track because the Tableau design has finished first and project slack.
The issue is cleared up because the Microstrategy programmer
put in an extra hour during the time period, and slack was available.
Status Report: Ending Period Four
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI |  | CPI%
A | 100% | 500 | 500 | 500 | 0 | 0 | 1 | 1 | 1 | 0%
B | 100% | 500 | 500 | 500 | 0 | 0 | 1 | 1 | 1 | 0%
C | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1 | 1 | 0%
D | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1 | 1 | 0%
E | 100% | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1 | 1 | 0%
F | 100% | 400 | 600 | 400 | -200 | 0 | 0.66667 | 1 | 1 | 33.33%
G | 100% | 600 | 600 | 600 | 0 | 0 | 1 | 1 | 1 | 0%
H | 100% | 800 | 900 | 800 | -100 | 0 | 0.88889 | 1 | 1 | 11.11%
I | 80% | 600 | 600 | 600 | 0 | 0 | 1 | 1 | 1 | 0%
J | 80% | 600 | 600 | 600 | 0 | 0 | 1 | 1 |  | 0%
Cumulative Total |  | 5800 | 7300 | 6400 | -300 | 0 | 0.95062 | 1 | 0% | 4.938%
Notes: The server set back the Microstrategy dashboard design, but extra hours by the
programmer as well as project slack did not cause an overall adverse affect on the project.
The Senior Analyst need to spend an additional hour in period four back documenting the
process, but the ADW and EDW data wharehouse connections were not delayed. The project
slack and ability to add extra hours to the project has quelled the overall server issue.
Step 1. You should develop the baseline for the entire project (see Fig 13.8), should be the cost baseline from Session 6.
Step 2. You can pick a time period approximately 1/3 the way through the project. If your project is highly complicated, you might pick a shorter period of time; we just need a planned number to compare to.
Step 3. You can introduce some problems that cause your project to be behind. Don't spend a great deal of time on developing this. Just create some delays or even some advances that change those actual costs.
Step 4. Then calculate the SV, CV, SPI, & CPI for the project at that point in time. See pages 463-472. Show it in a table like Table 13.2 on page 470.
Step 5: Write a brief status report, 2-3 paragraphs, explaining the various EVA indices and variances and what they tell you about the status of the project at that time.
Status Report 1.4
Period one finished without any issue, there was five hours of slack for activities A and B but there was no need to utilize the slack. Period two introduced the backwriting component of the project and serves as a natural check for code writing. The third period suffered a server issue that resulted in the activity cose being hire and completion was delayed.
Server issues at Target are not an uncommon issue, especially in the data structure for MicroStrategy. Many buyers and senior buyers at Target query from this server , which is why the delay and issues persist. The initial planned value whas only $400 because this is the easiest dashboard to create and design for the overall project. At the end of the third time period only 80% of the activity was completed, which resulted in the earned value equalling $320. GIven the project structure, there was slack for this activity and one hour was used in this instance, which resulted in the actual cost being an extra $100. The cost variance is a negative $180 becuase an extra hour was added and the activity was only 80% complete. In addition, the schedule variance was behind -80. The CPI and SPI metrics show this activity is behind schedule and overcost. I created a percentage metric that simply takes 1 minus the CPI and SPI values. This shows for the cumalative CPI the project is over budget by 5% and the schedule is behind by 3% compared to the current planned value.
Period four shows that the server issue did not proceed into this time period except for an additional hour of documentation for the senior analyst. This back documentation does not inhibit the work for the ADW and EDW data wharehouse connections, becuase the re was slack for activity F.

## Sheet2
|  | ACT | PV
| Mon | A | 73
| Tue | B | 73
| Wed | C | 73
| Thu | D | 73 | 148
| Fri | E | 73 | 108
| Sat | F | 73 | 163
| Sun | G | 73 | 91
3
1
| Total Posts | 514 |  | 514
73.4286
Express our progress on this weeks DB (a single 7-day activity) at end-of-day (EOD) Weds in terms of EV.
Use 7 day activity duration, last week’s total TBD posts (PV) allocated evenly per day, dollarize posts - $1/post. Actual costs each day are A, B, C, D, E, F, S (M - Su). Use % complete as the # of posts EOD Weds (TBD).
What is EV, CV, SV, CPI and SPI? What would a status report highlight?
Responses are due no later than midnight Friday on this thread.