## Sheet1
[16 empty] | Nbr of Posts Week 7 | Avg Daily Posts Week 7 | Avg Daily Cost Week 7
[16 empty] | 514 | 73.4286 | 73.4286 | 293.7143 | 0.50389
Task | Dur (in days) | Ttl PV | PV EOD Wed | #Posts EOD Wed | AC | Pct Complete | EV | CV | SV | BAC | EAC | ETC | VAC | CPI (EV/AC) | SPI (EV/PV)
DB Posts | 7 | 514 | 294 | 148 | 148 | 50.34% | 148 | 0 | -146 | 294 | 294 | 146 | 0 | 1 | 0.5034 | 61 | 5 | 56 |  | 148
[16 empty] | 54 | 17 | 37 |  | 108
|  |  | 73.4286 | [12 empty] | 45 |  | 45 |  | 163
|  |  | 293.7143 | [12 empty] | 1 |  | 1 |  | 91
[16 empty] | 1 |  | 1 |  | 3
[16 empty] | 9 | 1 | 8 |  | 1
[16 empty] | 171 | 23 | 148 |  | 514

## Sheet2
Task | Dur (in days) | Ttl PV | PV EOD Wed | #Posts EOD Wed | AC | Pct Complete | EV | CV | SV | CPI (EV/AC) | SPI (EV/PV)
DB Posts | 7 | 514 | 294 | 148 | 148 | 50.34% | 148 | 0 | -146 | 1 | 0.5034
A status report would highlight that the DB Posts activity is behind schedule by about 50%. However, because the planned base line was determined by the total number of posts from the previous week and then spread evenly over the duration number of days (7), the conclusion that the activity is behind schedule is based upon the assumption that work on the activity is evenly distributed over the number of days. Therefore, there is opportunity to complete the activity on time if the work per day increases.